## Project Planner
Project Title
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
initiating | 1 | 12 | 1 | 12 | 100%
Appoint a project manager | 1 | 3 | 1 | 3 | 100%
Develop project charter | 4 | 5 | 4 | 4 | 100%
Meet with the teammates | 9 | 4 | 9 | 4 | 100%
planning | 13 | 15 | 13 | 15 | 100%
Write the description about the scope plan | 13 | 4 | 13 | 3 | 100%
Create WBS and schedule | 16 | 5 | 15 | 6 | 100%
write design system components | 18 | 2 | 18 | 2 | 100%
craete a gantt chart | 16 | 10 | 13 | 10 | 100%
planning user interface design | 25 | 3 | 22 | 6 | 100%
Design tasks | 28 | 15 | 28 | 15 | 100%
design the software components | 28 | 5 | 28 | 5 | 100%
design the application layout | 33 | 5 | 33 | 6 | 100%
Design a list used for data analysis | 38 | 5 | 39 | 4 | 100%
Executing | 43 | 10 |  |  | 0%
linking database with the application | 43 | 2 |  |  | 0%
creating the background querry bank | 45 | 4 |  |  | 0%
check the data analysis | 49 | 1 |  |  | 0%
install new software on the server | 50 | 2 |  |  | 0%
install new SW on the clients machine | 52 | 1 |  |  | 0%
Testing | 53 | 5 |  |  | 0%
Document test cases for all Subsystems | 53 | 3 |  |  | 0%
Gather test data based on iteration | 54 | 4 |  |  | 0%
System analysts perform test | 55 | 2 |  |  | 0%
Show the client his first deliverables | 56 | 1 |  |  | 0%
Perform user acceptance testing procedures | 56 | 2 |  |  | 0%
Write reports of test results | 54 | 5 |  |  | 0%
Controlling | 57 | 3 |  |  | 0%
Keep updates the Status | 57 | 2 |  |  | 0%
Update plans | 59 | 1 |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%